|  | 2016 |
| --- | --- |
|  | Milton Keynes University Hospital NHS Trust |

Business case process

This document sets out the processes for business case preparation, approval and monitoring which are in accordance with the Trust’s Standing Financial Instructions. The current business case templates and documents are embedded documents in this paper and these should be used unless otherwise agreed. All communication and questions regarding business cases for both capital and revenue should be routed to business.cases@mkuh.nhs.uk

Business case approval process: overview

New funding request or change

No

Yes

Is there budget?

New Funds Are Required

Reutilise Existing Budget

C Prepare Capital Business Case

apital Business Case

Prepare Revenue Business Case

apital Business Case

Approval by ED (available weekly)

Go to page 2

Capital or Revenue?

Is value > £5,000?

AND

Useful life of > 2 years?

No

Yes

Value of change is GREATER than £10k Pay and/or £5k non-pay

Value of change is LESS than £10k Pay and/or £5k non-pay

No further approval required – treat as normal budget

Pay

Non-pay or Revenue?

- Business case preparation

Divisional Financial Business Partner needs to sign-off financials before submission

A business case should be prepared using the standard MKUH template (for cases up to £100k there is a Short-form Template, all others use the Standard Template).  The business case author should ensure that all relevant stakeholders are consulted and this is documented in the paper and that the financial input is signed off by the relevant Financial Business Partner.  Once prepared the business case should be sent to the Financial Programme Manager (FPM) at business.cases@mkuh.nhs.uk.  The case will be logged and issued with a unique reference which will be used to track the case’s progress through the various approval levels.  The FPM will be responsible for version control and ensuring feedback is recorded and integrated into the business case as it is progressed towards approval.  The FPM will ensure that the case is reviewed and sign-off is completed before being submitted for approval.

Prepare Business Case using standard Trust template

Note: there is an optional first step for revenue cases to take short case to ED’s for recommendation prior to completing full template this should be used if the writer is unclear on whether a business case would be supported

Business case submitted to business.cases@mkuh.nhs.uk

and FPM will log and a unique identifier is issued

(Note: all business cases must be routed through FPM not direct to ED/Management Board/CBIG/CCG)

Business case reviewed by FPM before submitting for approval/recommendation to ensure complete and accurate

Approval Process

(see detailed approval process below)

Item is not in capital or revenue plan

Go to Page 4

Item is in capital plan

Go to Page 3

FPM will forward for approval only after detailed review ensuring business case is complete and accurate and functional sign-off  is complete

Strategic cases

Go to Appendix 2

For medical equipment the case should be shared with the Medical Equipment & Training Manager for input

- Business case approval process for capital expenditure for items in the Capital Plan

(see Appendix 1 for Capital Plan approval process)

Emergency cases up to £1m

(note: can use emergency template if standard template not already prepared)

Non-urgent Business Cases

Is the Business Case <£100k?

Yes

£5-100k

No

>£100k

Director of Finance and Chief Executive for approval

Dra

Clinical Board Investment Group (CBIG) for recommendation

(note BAU only not strategic)

Capital Control Group (CCG) for approval

Management Board for approval

£100k to £1m

Trust Board for approval

>£1m

Finance & Investment Committee for recommendation

Approved (see page 5 Capital Execution and Monitoring)

Approved (see page 5 Capital Execution and Monitoring)

Approved - reported to Management Board “to note”

(see page 5 Capital Execution and Monitoring)

Only for capital over £1m

- Request for capital not in the capital plan or new revenue expenditure not in Budget

Emergency cases up to £0.5 m

(note: can use emergency template if standard template not already prepared)

Non Urgent Business Cases

Executive Directors meeting for recommendation

Order interchangeable of submission to ED’s and CBIG (suit to timing of meetings)

Clinical Board Investment Group (CBIG) for re prioritisation /recommended from contingency

DoF and Chief Exec for  approval and/or Executive Directors

Approved (go to page 5 Capital Execution and Monitoring)

Management Board for approval

Up to £500k

Approved - reported to Management Board “to note”

(see page 5 Capital Execution and Monitoring)

Only for items over £500k

Finance & Investment Committee for recommendation

Approved (go to page 5 Capital Execution and Monitoring)

Trust Board for approval

>£500k

- Capital spend execution and monitoring

Once a business case is approved the following process is followed:

Finance Programme Manager (FPM) will inform the business case owner of the approval of their business case

CAPITAL

Business case owner to complete a Capital Order Form & submit a Quotation, PPQ (Medical Equipment only) and E-Form (Medical Equipment only)

and email to:

capital.orders@mkuh.nhs.uk

REVENUE

Finance will adjust the relevant budget in line with the approved business case

Expenditure incurred and monitored as part of normal budget monitoring

Capital Coordinator reviews the order form, and, if complete, places in Finance ‘Pending’ Folder on shared Capital drive.

Items of medical equipment are reviewed by the

Medical Equipment & Training Manager to ensure the equipment is in consistent with other Trust equipment

Capital Coordinator to populate Medical Equipment Tracker

Page 6

Finance rep reviews order form, and populates final section on form.  Once approved and budget verified, form is placed in ‘Approved’ folder on shared Capital drive

Capital Coordinator to input requisition on SBS Oracle

Purchasing Dept to review requisition and create a Purchase Order

Capital Coordinator to input order details onto RAM (Asset Tracking System)

Capital Coordinator to receipt order on SBS Oracle once invoice has been received or when business case owner can advise goods have been delivered

Capital Coordinator to maintain RAM with updated receipting information

Projects are monitored throughout the year by FPM in conjunction with business case owner/project manager

Monthly reports to business case owner of spend versus plan

Appendix 1

Capital Plan Approval Process

Capital expenditure is approved as part of the annual planning process.  Capital is classified as either:

- Business as Usual (BAU) which is to maintain the estate and infrastructure of the Trust on an ongoing basis.  This type of capital is funded by the Trust out of its own resources.

- Strategic Capital which is to make large scale capital investments to develop the estates and infrastructure of the Trust.  This type of capital investment would normally require additional funding either from the DoH of some other source.

The level of the both types of expenditure is set out in the annual plan and approved by the Board ahead of the start of the financial year.

The constituents of the BAU capital plan is derived through the following process:

Capital bids assembled by Divisions and Directorates and scored using standard scoring system in line with Trust Objectives and with reference to the Trust Risk Register

Scored capital bids from Divisions and Directorates submitted to CBIG and prioritisation finalised within the Trust’s financial envelope for BAU capital

CBIG prioritised capital plan submitted to ED’s for recommendation

Capital plan authorised by Management Board to form the BAU Annual Capital Plan

Appendix 2

Strategic Projects Approvals Process

Urgent Strategic Business cases

Is the project under £1m

Non-Urgent Strategic Business Cases

- For urgent cases

Strategic Modernisation Programme Board (SMPB) for recommendation.

Draft

Director of Finance and Chief Executive for approval

Is the Business Case over £1m

Yes

Management Board for Recommendation and Trust Board for Approval

No

Management Board for Approval

Approved – reported to Management Board to note

(see page 5 for Capital Execution and Monitoring)

Appendix 3

Investment  Limits Trust SFI’s (Standing Financial Instructions)

The table below highlights the spend authority limits by the various boards.

| Board | Limits | Capital | Revenue |
| --- | --- | --- | --- |
| Clinical Board Investment Group (CBIG) | All | Recommendation only | Recommendation only |
| Executive Directors | Up to | £50,000 | n/a |
| Capital Control Group | Up to | £100,000 | n/a |
| Management Board | Up to | £1,000,000 | £1,000,000 |
| Trust Board | Greater than | £1,000,000 + | £1,000,000 + |
| Other Boards and Committees |  |  |  |
| Strategic Modernisation Programme Board | Recommendation Only - Business cases to be presented at Management Board and Trust Board based on authority Limits. |  |  |
| Finance & Investment Committee | For review and information purposes only. |  |  |

If items are not in capital plan then only Management Board and Trust Board can authorise and authority levels are halved.

Raising a Capital Order