## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
144707 | 18/EM/0190 | 243165 | AEGIS II A phase 3, multicentre, double-blind, randomised, placebo-controlled, parallel-group study to investigate the efficacy and safety of CSL112 in subjects with Acute Coronary Syndrome. " | No |  | 122 |  |  | 2017-11-04 | 2018-07-20 | 2018-09-14 | 2018-11-13 | 2018-11-19 | Please Select... | 2018-12-14 | D - Sponsor Delays | The delay occurred due to organising of the Site Initiation Visit and limited availability of the training sessions. | Sponsor
144708 | 18/SC/0243 | 240684 | ORION 4 | Yes | 2019-04-30 | 91 | 88 | 179 | 2018-05-14 | 2018-11-02 | 2018-10-17 | 2019-01-20 | 2019-02-01 | Please Select... | 2019-04-29 | D - Sponsor Delays | Sponsor setting up clinic dates | Sponsor
144709 | 15/SC/0103 | 240684 | "SCALOP-2: Systemic therapy and Chemoradiation in Advanced Localised Pancreatic cancer -2" | Yes | 2019-03-31 | 104 | 12 | 116 | 2018-11-15 | 2018-12-05 | 2019-03-14 | 2019-03-05 | 2019-03-19 | Please Select... | 2019-03-19 | J - Other | Shared care agreement | Both
144710 | 18/LO/0123 | 235034 | CHESS | Yes | 2019-05-01 | 67 | 1 | 68 |  | 2019-02-22 | 2019-02-22 | 2019-04-30 | 2019-04-30 | Please Select... | 2019-05-01 | D - Sponsor Delays |  | Sponsor
146745 | 18/SC/0247 | 230545 | Managing Avascular Necrosis Treatments: an Interventional Study: MANTIS | Yes | 2019-07-10 | 64 | 91 | 155 | 2018-11-05 | 2019-02-05 | 2018-06-26 | 2019-04-16 | 2019-04-10 | Please Select... | 2019-04-16 |  |  | Please Select...
146746 | 18/EM/0310 | 239782 | C-Stich2: Emergency Cervical Cerclage to Prevent Miscarriage and Preterm Birth: a Randomised Controlled Trial | No |  | 144 |  |  | 2018-09-12 | 2018-10-19 | 2019-11-16 | 2019-03-12 | 2019-03-12 | Please Select... | 2019-03-12 | J - Other |  | Both
146747 | 16/EM/0172 | 194491 | Non-vitamin K antagonist Oral anticoagulants in patients with Atrial High rate episodes | No |  | 71 |  |  | 2017-04-27 | 2019-02-28 | 2016-05-24 | 2019-05-10 | 2019-05-10 | Please Select... | 2019-05-10 |  |  | Please Select...