## MKUH Q4 2019-20
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
163424 | 19/LO/0842 | 259611 | REACH-UP | Yes | 2020-02-17 | 30 | 12 | 42 | 2019-11-22 | 2020-01-06 | 2019-09-04 | 2020-02-05 | 2020-02-05 | Please Select... | 2020-02-05 |  |  | Please Select...
163425 | 19/EM/0264 | 266058 | FAME | Yes | 2020-07-06 | 152 | 154 | 306 | 2019-08-15 | 2019-09-04 | 2019-09-03 | 2020-01-21 | 2020-02-03 | Please Select... | 2020-02-07 |  |  | Please Select...
163426 | 18/YH/0358 | 242342 | The Sunflower Study | Yes | 2020-03-06 | 240 | 21 | 261 | 2019-06-19 | 2019-06-19 | 2018-12-12 | 2020-02-12 | 2020-02-14 | Please Select... | 2020-02-14 | E - Staff availability issues | Site PI | NHS Provider
163427 | 20/EE/0101 | 281712 | The Recovery Trial | Yes | 2020-04-06 | 1 | 10 | 11 | 2020-03-16 | 2020-03-26 | 2020-03-17 | 2020-03-27 | 2020-03-27 | Please Select... | 2020-04-02 |  |  | Please Select...
164543 | 18/LO/0660 | 237150 | REMAP-CAP | No |  | 190 |  |  | 2019-01-21 | 2019-10-08 | 2018-07-23 | 2020-04-07 | 2020-04-15 | Please Select... | 2020-04-24 | H - Contracting delays | Contract | Both

## MKUH Q1 2020-21
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
164543 | 18/LO/0660 | 237150 | REMAP-CAP | No |  | 190 |  |  | 2019-01-21 | 2019-10-08 | 2018-07-23 | 2020-04-07 | 2020-04-15 | Please Select... | 2020-04-24 | H - Contracting delays | Contract | Both

## MKUH Q2 2020-21
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
164549 | 18/SC/0242 | 238151 | BLING III | Yes | 2020-10-09 | 135 | 91 | 226 | 2020-02-03 | 2020-02-26 | 2018-09-17 | 2020-03-30 | 2020-07-10 | Please Select... | 2020-07-10 | E - Staff availability issues | Pharmacy (Clinical Trial Pharmacist vacancy) | NHS Provider
164550 | 20/WM/0054 | 264593 | CRAFFT- Children's radius acute fracture fixation trial | No |  | 171 |  |  | 2020-02-21 | 2020-02-21 | 2020-04-16 | 2020-03-17 | 2020-08-10 | Please Select... | 2020-08-10 | J - Other | COVID-19 | Neither