## Performance in Initiating Q3
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to: | Options
45705 | 20/EE/0127 | 277059 | HUSH - The Humeral Shaft Fracture Trial | YES | 2020-10-31 | 71 | 83 | 83 | 2020-07-16 | 2020-07-23 | 2020-06-02 | 2020-09-30 | 2020-10-02 | N/A | 2020-10-02
45217 | 20/NW/0234 | 276873 | SOFFT: Simple Olecranon Fracture Fixation Trial |  | 2021-01-21 | 131 |  |  | 2020-07-10 | 2020-07-10 | 2020-06-16 | 2020-10-14 | 2020-11-18 | n/a | 2021-04-27
45718 | 20/NS/0059 | 282870 | PACE | Yes | 2020-12-15 | 14 | 19 | 19 | 2020-04-28 | 2020-11-12 | 2020-05-04 | 2020-11-13 | 2020-11-26 | N/A | 2020-11-26

## Performance in Initiating Q4
ID | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to: | Options
[6 empty] | xxx | xxx | xxx
[6 empty] | xxx | xxx | xxx
[6 empty] | xxx | xxx | xxx

## Performance in Delivery Q3
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments | Options
37129 | 18/SC/0005 | 234377 | INGR1D | Yes | 1500 | 1500 | Yes | 2021-01-30 | 3356 | 2020-11-01 | 3356 | recruitment complete
11988 | 11/SW/0222 | 86041 | PRED4 | No | 0 | 0 | Yes | 2017-05-18 | 4 | 2020-12-31 | 9 | recruitment complete

## Performance in Delivery Q4
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments | Options
18346 | 14/EE/1293 | 164389 | C-stich | YES | 5 | 15 | 2018-04-01 | Yes | 9 | 2021-01-31 | 24 | recruitment completed
36043 | 17/NS/0018 | 223787 | Future-HTA | YES | 28 | 56 | 2018-05-31 | Yes | 6 | 2021-01-31 | 6 | recruitment completed | change of PI led to delays
45571 | 20/NW/0212 | 282655 | Pan-Covid | Yes | 0 | 0 | 2021-03-01 | Yes | 38 | 2021-03-31 | 42 | recruitment completed
19626 | 15/WM/0268 | 180518 | ENRICH | Yes | 1 | 2 | 2017-08-15 | Yes | 1 | 2021-03-31 | 2 | recruitment completed | rare disease study
45718 | 20/NS/0059 | 282870 | PACE | Yes | 5 | 15 | 2020-12-31 | Yes | 6 | 2021-02-28 | 10 | recruitment completed