## Performance in Initiating
System generated fieldId | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
195242 | 20/YH/0232 | 280105 | ATNEC | Yes | 2021-08-17 | 55 | 146 | 201 | 2020-09-14 | 2021-01-28 | 2020-10-22 | 2021-03-10 | 2021-03-24 | Please Select... | 2021-07-19 | J - Other | covid | Neither
195258 | 19/SS/0040 | 255113 | TARGET CTCA | Yes | 2021-08-18 | 37 | 7 | 44 | 2021-05-18 | 2021-07-05 | 2020-10-21 | 2021-07-17 | 2021-08-11 | Please Select... | 2021-08-23 | J - Other | covid | Neither
195259 | 20/LO/0238 | 265114 | RADAR | Yes | 2021-11-01 | 14 | 147 | 161 | 2020-09-15 | 2021-05-24 | 2020-05-15 | 2021-06-07 | 2021-06-07 | Please Select... | 2021-06-08 | J - Other |  | Neither
195260 | 21/NE/0114 | 301115 | Preg-Cov | Yes | 2022-01-05 | 41 | 86 | 127 | 2021-06-07 | 2021-08-31 | 2021-07-29 | 2021-09-22 | 2021-10-11 | Please Select... | 2021-11-09 |  |  | Please Select...
195261 | 20/SC/0372 | 283157 | CRASH 4 | No |  | 134 |  |  | 2021-06-25 | 2021-07-05 | 2020-10-17 | 2021-10-14 | 2021-11-16 | Please Select... | 2021-12-01 |  |  | Please Select...
195439 | 21/WA/0030 | 293576 | SEARCH | Yes | 2021-11-25 | -99 | 198 | 99 | 2021-08-18 | 2021-08-18 | 2021-03-12 | 2021-04-07 | 2021-05-11 | Please Select... | 2021-05-11 |  |  | Please Select...
195441 | 21/SC/0122 | 266600 | REMODL-A | No |  | 1 |  |  | 2019-08-11 | 2021-06-15 | 2021-06-14 | 2021-06-09 | 2021-06-16 | Please Select... | 2021-10-22 | H - Contracting delays | CT arrangements | NHS Provider

## Performance in Delivering
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
57816 | 17/ES/0071 | 213164 | Cardiac Care | Range Agreed | 3 | 5 | Not Available / Not Agreed |  | 0 | 2021-11-01 | 0 | Withdrawn By Sponsor | Closed due Covid
57817 | 18/NW/0736 | 251961 | Psoriasis Study of Health Outcomes (PSoHO) – an International Observational Study of 3-Year Health Outcomes in the Biologic Treatment of Moderate-to-Severe Plaque Psoriasis | Range Agreed | 0 | 10 | Not Available / Not Agreed |  | 0 | 2021-05-01 | 0 | Withdrawn By Sponsor | closed due Covid