## Performance in Initiating
System generated fieldId | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
204205 | 21/WM/0172 | 291236 | SNAP-3 | Yes | 2022-05-16 | 96 | 104 | 200 | 2021-07-13 | 2021-10-28 | 2021-09-13 | 2022-03-03 | 2022-02-01 | Please Select... | 2022-04-07 | J - Other |  | Neither
204206 | 21/SC/0274 | 293939 | Translate | No |  | 70 |  |  | 2021-11-01 | 2022-02-10 | 2021-09-14 | 2022-04-26 | 2022-04-21 | Please Select... | 2022-05-06 | J - Other | Waiting for LAPT tests to be set up at MKUH | NHS Provider

## Performance in Delivering
System generated fieldId | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
60169 | 17/ES/0071 | 213164 | Cardiac Care | Range Agreed | 3 | 5 | Not Available / Not Agreed |  | 0 | 2021-11-01 | 0 | Withdrawn By Sponsor | Closed due Covid
60374 | 14/WA/1056 | 154468 | AML-19 | Number Agreed | 11 | 11 | Date Agreed | 2021-10-29 | 9 | 2021-10-29 | 79 | Withdrawn By Sponsor | none